## READ FIRST
PURPOSE OF THE DOCUMENT
This document provides a high level estimation of the timing required to implement KINTO Share service. It is based on the "Delivery approach" document, also part of this toolkit. The exact timing and scope of detailed activities might change from market to market. The activities in this document can be used as a baseline to be customized and adapted based on the scope of each market. Some activities are only applicable to markets which already have a service in place that should be migrated on the pan-e platform. Such activities are indicated with a "*" sign.

## High level timing plan
| Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
ONBOARDING | bar: Month 1 Q1 to Month 1 Q4
. PAN-E PRODUCT VISION AND SERVICE PRESENTATION | bar: Month 1 Q1
. DEFINITION OF SERVICE MODEL AND USE CASES | bar: Month 1 Q1 to Month 1 Q4
. DEALER IDENTIFICATION AND ONBOARDING | bar: Month 1 Q2 to Month 1 Q4
. GOALS SETTING | bar: Month 1 Q4
. DELIVERY PLAN DEFINITION | bar: Month 1 Q4
READINESS | bar: Month 2 Q1 to Month 3 Q1
. PRODUCT APPROVAL | bar: Month 2 Q1
. GAPS ASSESSMENT | bar: Month 2 Q1 to Month 2 Q3
. JOURNEY ANALYSIS | bar: Month 2 Q1 to Month 2 Q3
. PROCESSES ANALYSIS | bar: Month 2 Q1 to Month 2 Q3
. SYSTEM MAPPING | bar: Month 2 Q4 to Month 3 Q1
. CUSTOMER SUPPORT MODEL AND PROCEDURES DEFINITION | bar: Month 2 Q2 to Month 2 Q4
. KPI DEFINITION | bar: Month 2 Q4 to Month 3 Q1
. LEGAL ASSESSMENT | bar: Month 2 Q2 to Month 3 Q1
. MARKETING & COMMUNICATION STRATEGY DEFINITION | bar: Month 2 Q3 to Month 3 Q1
. MIGRATION STRATEGY DEFINITION * | bar: Month 2 Q4 to Month 3 Q1
. DEFINITION OF IMPLEMENTATION PLAN | bar: Month 3 Q1
IMPLEMENTATION | bar: Month 3 Q2 to Month 4 Q2
. LOCAL INTEGRATIONS | bar: Month 3 Q2 to Month 4 Q1
. TRANSLATIONS | bar: Month 3 Q2 to Month 3 Q4
. HARDWARE INSTALLATION | bar: Month 3 Q2 to Month 3 Q4
. PLATFORM CONFIGURATION | bar: Month 3 Q2 to Month 3 Q4
. APP CONTENT | bar: Month 3 Q3 to Month 3 Q4
. UAT | bar: Month 4 Q1 to Month 4 Q2
. DATA MIGRATION * | bar: Month 3 Q4
. OBU MIGRATION * | bar: Month 3 Q2 to Month 3 Q4
. APP MIGRATION * | bar: Month 3 Q3 to Month 3 Q4
. DEALER OPERATIONS | bar: Month 3 Q4 to Month 4 Q1
. SERVICE MONITORING | bar: Month 3 Q4 to Month 4 Q2
. WEBSITE | bar: Month 3 Q4 to Month 4 Q2
. GO LIVE PLANNING | bar: Month 4 Q2
DEPLOYMENT | bar: Month 4 Q3 to Month 5 Q4
. TRAINING | bar: Month 4 Q3 to Month 4 Q4
. PROD ENVIRONMNET ACTIVATION | bar: Month 4 Q3 to Month 4 Q4
. APP MIGRATION * | bar: Month 4 Q3 to Month 4 Q4
. WEBSITE | bar: Month 4 Q3 to Month 4 Q4
. COMMUNICATION | bar: Month 4 Q3 to Month 5 Q3
. GO LIVE | bar: Month 5 Q1
. LEGAL * | bar: Month 5 Q1
. PLATFORM MIGRATION * | bar: Month 5 Q2 to Month 5 Q4
* Activities applicable only to markets migrating from an existing service and provider

## 1. Onboarding
AREA | TASK | STATUS | EST. DURATION | START DATE | END DATE
PAN-E PRODUCT VISION AND SERVICE PRESENTATION | High level presentation of dealer model | COMPLETED | Each market to fill based on scope agreed
Pan-e platform presentation
DEFINITION OF SERVICE MODEL AND USE CASES | Service model and use cases definition
Fleet sizing and selection
Target customers identification
High level communication strategy identified
Organizational model presented and defined
Pricing model definition
Financial plan definition
DEALER IDENTIFICATION AND ONBOARDING | Contact with potential pilot dealers
Service initial induction
Formal commitment for pilot phase
GOALS SETTING | Setting of key targets for pilot phase
Validation of targets with all stakeholders
DELIVERY PLAN DEFINITION | Definition of high level plan for service activation

## 2. Readiness
AREA | TASK | STATUS | EST. DURATION | START DATE | END DATE
PRODUCT APPROVAL | Product approval document shared
Product approval review and validation
GAPS ASSESSMENT | Identification of key areas of attention
Definition of any local legal or tax requirements
Gaps discussion and validation with product team
JOURNEY ANALYSIS | Analysis and mapping of local requirements (tax, legal or configurable items)
Definition of configurations of the journey based on local requirements
CJ and CX validation
PROCESSES ANALYSIS | Analysis of local processes
Requirements definition
Definition of TO BE processes to support the journey defined
SYSTEM MAPPING | Definition of systems architecture and technical requirements to enable processes
Identification of local integrations required
Definition of suppliers for local integrations (e.g. CMS/ERP)
CUSTOMER SUPPORT MODEL AND PROCEDURES DEFINITION | Sharing of standard customer organizational model and support procedures
Definition of local model for customer support
Identification of provider for customer support
Localization of operative procedures
KPI DEFINITION | Analysis of pan-e standard KPIs
Definition and configuration of any local KPI
LEGAL ASSESSMENT | Sharing of pan-e legal pack by KINTO Eu
Analysis by local legal department
Validation of subcontract agreement
Validation of terms and conditions
Validation of privacy notice
MARKETING & COMMUNICATION STRATEGY DEFINITION | Localization of pan-e marketing journeys
Local marketing strategy definition
Identification of owners for implementation of marketing plan
Definition of communication strategy for the launch of the service
MIGRATION STRATEGY DEFINITION * | Definition of data migration strategy
Definition of app migration strategy (app store)
Definition of OBUs migration strategy
DEFINITION OF IMPLEMENTATION PLAN | Definition of plan for the implementation phase
* Activities applicable only to markets migrating from an existing service and provider

## 3. Implementation
AREA | TASK | STATUS | EST. DURATION | START DATE | END DATE
LOCAL INTEGRATIONS | Enabling of local integrations (e.g. CRM, ERP, etc.)
TRANSLATIONS | Lokalize tool shared by KINTO EU (to manage translations)
Customer interface (app) translated in local language
Back office (private and business) translated in local language
Translation of Vubox installation manual
HARDWARE INSTALLATION | Vubox cables sending and reception
Vehicles keys collection
Vuboxes reception
Welding of keys
Vubox shipment to dealers
Training of dealer personnel by Vulog technician
Vuboxes installation on vehicles
Communicate to Vulog vechiles plates associated to Vubox
PLATFORM CONFIGURATION | Set up of local instance for the back office
Local configuration for fleet managemetn app
Local fleets configuration on the EU app
Local Stripe account configuration
User roles defined and configuration
Pricing model configuration
Booking timings and rules definition
Models and vehicles configuration
Parkings configuration
Promotions configuration
System emails mapped and configuration
Email content update
Content uploaded (e.g. vehicles icons)
APP CONTENT | T&Cs, Privacy Policy and FAQs updated on the app
UAT | App UAT
Back office and fleet app UAT
Local processes UAT
Local integrations UAT (Stripe, CMS, etc.)
DATA MIGRATION * | Freeze new registrations and customer profiles update on existing app
Local supplier to send the last updated customer DB extract + documents/images
Vulog to import customer DB profile and data quality check
OBU MIGRATION * | Installation of Vuboxes on the fleet as defined in previous phase
APP MIGRATION * | Implementation of the app migration strategy as defined in previous phase
DEALER OPERATIONS | Identification of resources within the dealer organization
SERVICE MONITORING | Activation of local instance for the KPI monitoring tool
WEBSITE | Website content update
GO LIVE PLANNING | Go live plan confirmation
* Activities applicable only to markets migrating from an existing service and provider

## 4. Deployment
AREA | TASK | STATUS | EST. DURATION | START DATE | END DATE
TRAINING | Training of dealer staff
Training of CC operators
Training of the Control Room
PRODUCTION ENVIRONMNET ACTIVATION | Fleet activation in the PROD environment
APP MIGRATION * | End of life functionality activation (force update of new app)
WEBSITE | Activation of Vulog portal on the website
COMMUNICATION | Implementation of the communication strategy defined
GO LIVE | Service activation
LEGAL * | Notify existing users of T&C and Privacy Policy update
PLATFORM MIGRATION * | Switch off of local platform
SERVICE MONITORING | Monitoring of potential issues or bugs after the activation
Customer support cases analysis
* Activities applicable only to markets migrating from an existing service and provider